## Project Goal & Objectives
PROJECT GOAL STATEMENT
PROJECT NAME | Capstone 2022 | Date Created | 2022-01-17
Team Members | Wiktoria Biernat (W0427844), Cassandra Curtis (W0449188), Josh Jones (W0446531), Mark Moulton (W0440932), Rose Scoville (W0249159)
TEST GOALS & OBJECTIVES AGAINST SMART CRITERIA
SPECIFIC • MEASURABLE • ACHIEVABLE • RELEVANT • TIME-BOUND
GOAL STATEMENT | To develop a Unity-based virtual pet simulator by the end of the Winter 2022 semester according to Capstone project requirements, which gives users the opportunity to hatch and raise a virtual pet. Documents will be created outlining a hypothetical second phase wherein users can battle their virtual pets asynchronously with other users.
OBJECTIVE NO. | An objective should look like this: “To design a web interface to support application.” |  | Time Schedule | Responsible Member(s)
1 | Set up team communication channel for ongoing discussions and to collect documentation links. (COMPLETE) |  | Due Jan. 20 | Mark Moulton
2 | Project Manager to explore and set up project management tool(s) to organize and visualize project process and status for its full duration. (COMPLETE) |  | Due Jan. 20 | Rose Scoville
3 | Project Manager to explore and set up team's version control for development phase, link this to project management tool if possible. (COMPLETE) |  | Due Jan. 20 | Rose Scoville
4 | Collect brainstorming notes and team members' input on own strenghts/interests and weaknesses/disinterests. (COMPLETE) |  | Due Jan. 20 | Cassandra Curtis
5 | Establish each team member's role. (COMPLETE) |  | Due Jan. 20 | All project team members
6 | Project Manager to add deliverables, objectives, and tasks to project board and roadmap. |  | Due Jan. 20 | Rose Scoville
7 | Define minimum viable product to be developed, including feature list and requirements. |  | Due Jan. 20 | All project team members
8 | Dev Team to explore possible technology options and define project's stack. (COMPLETE) |  | Due Jan. 20 | All dev team members
9 | Project Manager to submit Deliverable 1: Project Goal Statement and Objectives doc to Client. (COMPLETE) |  | Due Jan. 20 | Rose Scoville
10 | Team to write formal Project Proposal. |  | Due Feb. 3 | All project team members
11 | Project Manager to submit Deliverable 2: Formal Proposal to Client. |  | Due Feb. 3 | Rose Scoville
12 | Define Milestone 1 requirements to be developed. |  | Due Feb. 17 | Wiktoria Biernat
13 | Define Milestone 2 requirements to be developed. |  | Due Feb. 17 | Wiktoria Biernat
14 | Define product user flow(s) to account for all minimum viable product requirements. |  | Due Feb. 17 | Rose Scoville
15 | Create minimum viable product wireframes for application pages. |  | Due Feb. 17 | Cassandra Curtis
16 | Create minimum viable product page mock-ups and prototype to show application flow. |  | Due Feb. 17 | Cassandra Curtis
17 | Team to write Project Plan. |  | Due Feb. 17 | All project team members
18 | Project Manager to submit Deliverable 3: Project Plan to Client. |  | Due Feb. 17 | Rose Scoville
19 | Dev team to research and familiarize with stack (Unity, WebGL, etc.). |  | Due Feb. 17 | All dev team members
20 | Code basic virtual pet v0.01 with placeholder art. All stats should be tracked, but no mini game at this point. |  | Due Feb. 24 | Mark Moulton
21 | Use v0.01 to design and hook up UI. |  | Due Feb. 28 | Cassandra Curtis
22 | Create a MySQL database. |  | Due Feb. 28 | Wiktoria Biernat
23 | Set up enviroment for website development. |  | Due Feb. 28 | Josh Jones
24 | Install and create deployment enviroment for website. |  | Due Feb. 28 | Josh Jones
25 | Create test database for the site during develpment (phpMyAdmin). |  | Due Feb. 28 | Josh Jones
26 | Project Manager to submit Deliverable 4: Milestone 1 Report to Client. |  | Due Mar. 3 | Rose Scoville
27 | Code simple minigame to meet requirements defined in Project Plan. |  | Due Mar. 14 | Wiktoria Biernat, Rose Scoville
28 | Hook up minigame score to database leaderboard. |  | Due Mar. 20 | Rose Scoville
29 | Setup basic functionality for communication between site and database. |  | Due Mar. 23 | Josh Jones, Wiktoria Biernat
30 | Establish connection to game through website. |  | Due Mar. 23 | Josh Jones, Mark Moulton, Wiktoria Biernat
31 | Deploy WebGL version to website for testing. |  | Due Mar. 23 | Josh Jones
32 | Project Manager to submit Deliverable 5: Milestone 2 Report to Client. |  | Due Mar. 24 | Rose Scoville
33 | Create Project Presentation. |  | Due Apr. 7 | Cassandra Curtis
34 | Team to present project to peers. |  | Due Apr. 7 | All project team members
35 | Project Manager to submit Deliverable 6: Project Presentation document to Client. |  | Due Apr. 7 | Rose Scoville
36 | Have a project post-mortem discussion. |  | Due Apr. 13 | All project team members
37 | Team to complete Project Reflections document. |  | Due Apr. 14 | All project team members
38 | Project Manager to submit Deliverable 7: Project Reflections document to Client. |  | Due Apr. 14 | Rose Scoville
| Team to complete Peer Review Document. |  | Due Apr. 14 | All project team members